## Slide 1
Ambisphere with hue
Project Plan
DM: zhonglong.chen
DATE: 2013-06-18

## Slide 2
Project Purpose
Requirements
Specification
Support item in detail & project expense
Project Schedule
Project support team
Content

## Slide 3
Control Ambiglow and Hue synchronously
Extend Ambiglow to Hue
Extend Ambimusic and Ambisphere to Hue
Project Purpose

## Slide 4
  HW
    Philips Hue
    Android smart phone
    Smart TV
      Panasonic sld3
  SW
    Smart TV Platform:
      Android 4.2
      Ambiglow control api, need TPE/vendor support
  UI
    UI design and resource
  Others
Requirements

## Slide 5
Specification
Category | Requirement | Priority | Description/Criteria
Hue | Control Hue via MyRemote | A | Control Hue feature, such as On/Off, brightness, Color etc.
 | Control Hue via smart TV | A | 
Ambiglow | Control Ambiglow via smart TV | A | Control Ambiglow feature, such as On/Off, brightness, Color etc.
 | Control Ambiglow via MyRemote | A | Control Ambilight via MyRemote server on smart TV
 | Extend Ambiglow to Hue | A | Change Hue automatically according to Ambiglow
Ambimusic/Ambisphere | Extend Ambilmusic to Hue | B | 
 | Extend Ambisphere to Hue | C | 

## Slide 6
Department | Man-power | Task
FW | 0.5人/month | Ambiglow feature implement and interface
 | 0.5人/month | Hue feature study and interface
 | 1人/month | Function on smart phone side
 | 1人/month | Function on TV side
UX | 0.5人/month | UX design on smart TV and phone
UI | 0.5人/month | Provide image resource for application
Support item in detail & project expense
Manpower Expense |  |  |  |  |  |  |  | Other Expense |  |  |  |  |  | 
EE (m*m) | Layout (m*m) | DQE (m*m) | UI (m*m) | FW (m*m) | ME (m*m) | LCM (m*m) | TTL (RMB) | Sample (RMB) | Tooling (RMB) | Biz Trip (RMB) | Certification & Royalty (RMB) | Training | Total (RMB) | XMIC Investment
 |  |  | 1 | 3 |  |  | 36,000 | 2500 |  |  |  |  | 2500 | 
TTL= 9000RMB/man*man*month + Sample + Biz Trip+…= 38,500 RMB |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 7
Project Schedule
milestone
Release Version 3
08/01
KO 05/21
Release Version 1
06/01
Release Version 2
07/01
 |  |  |  |  |  | 2013 June |  |  | 2013 July |  |  |  |  | 2013 August |  |  | 
Ambisphere with Hue |  |  |  |  |  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Period | Task | Content | Owner | Start Date | Due date | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26
UX/UI | UX |  | 连成 | 6月17日 | 7月1日 |  |  |  |  |  |  |  |  |  |  |  | 
 | GUI |  | 源远 | 7月1日 | 7月15日 |  |  |  |  |  |  |  |  |  |  |  | 
Feature | Function spec |  | 钟龙 | 6月10日 | 6月17日 |  |  |  |  |  |  |  |  |  |  |  | 
 | Hue feature study |  | 雯雯 | 6月17日 | 6月24日 |  |  |  |  |  |  |  |  |  |  |  | 
 | Hue implement | Hue control API | 雯雯 | 6月24日 | 7月1日 |  |  |  |  |  |  |  |  |  |  |  | 
 | Ambiglow implement | Ambiglow control API | 韦荣 | 6月17日 | 7月1日 |  |  |  |  |  |  |  |  |  |  |  | 
 | Ambiglow with Hue | on MyRemote Server | 钟龙 | 7月1日 | 7月8日 |  |  |  |  |  |  |  |  |  |  |  | 
 | Ambimusic with Hue |  | 钟龙 | 7月8日 | 7月15日 |  |  |  |  |  |  |  |  |  |  |  | 
 | Ambisphere with Hue |  | 钟龙 | 7月15日 | 7月22日 |  |  |  |  |  |  |  |  |  |  |  | 
App | Hue and ambifamily Service |  | 钟龙 | 7月22日 | 8月5日 |  |  |  |  |  |  |  |  |  |  |  | 
 | TV App with Hue |  | 钟龙 | 8月5日 | 8月19日 |  |  |  |  |  |  |  |  |  |  |  | 
 | Phone App |  | 雯雯 | 7月22日 | 8月5日 |  |  |  |  |  |  |  |  |  |  |  | 
Self-test |  |  |  | 8月19日 | 8月27日 |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 8
Project Team
Dep. | Chinese Name | Mainly Task | Ext | Email
FW | 陈钟龙 | Project Leader Smart TV hue control | 5754 | Zhonglong.chen@tpv-tech.com
 | 蔡雯雯 | Smart phone hue control | 8079 | Wen.cai@tpv-tech.com
 | 陈韦荣 | Ambi- interface implement | 82-3431 | Ronnie.chen@tpv-tech.com
UX | 陈连成 | UX on smart TV and phone | 5750 | Lch.chen@tpv-tech.com
GUI | 徐源远 | Image resource | 8925 | Agnes.xu@tpv-tech.com
PM | 刘婷 | PM | 5705 | Tanya.liu@tpv-tech.com

## Slide 9
Thank you!